## OOPSIE Team Report 4
Team | Task | Status | Activity | GoalDueDate | GoalCompletionDate | ActivityDate | Student | Hours | Minutes | Sprint | Pig
OOPSIE | Flyer Design | Completed | Worked on the brochure | 2024-02-07 |  | 2024-01-25 | Alia Othman | 3 |  | 1 | 1
OOPSIE | Flyer Design | Completed | Creating flyer | 2024-02-07 |  | 2024-01-30 | Alia Othman | 4 |  | 1 | 1
OOPSIE | Flyer Design | Completed | Flyer Design | 2024-02-07 |  | 2024-01-28 | Alia Othman | 2 | 30 | 1 | 1
OOPSIE | Flyer Design | Completed | Brochure Design | 2024-02-07 |  | 2024-01-29 | Alia Othman | 3 | 30 | 1 | 1
OOPSIE | Flyer Design | Completed | Changing The Flyer design | 2024-02-07 |  | 2024-02-02 | Alia Othman | 2 |  | 1 | 2
OOPSIE | Flyer Design | Completed | The first part of the flyer design | 2024-02-07 |  | 2024-02-04 | Alia Othman | 3 | 0 | 1 | 2
OOPSIE | Flyer Design | Completed | Finishing the flyer design | 2024-02-07 |  | 2024-02-06 | Alia Othman | 3 |  | 1 | 2
OOPSIE | Flyer Design | Completed | Team Report | 2024-02-07 |  | 2024-02-05 | Alia Othman | 3 |  | 1 | 2
OOPSIE | Flyer Design | Completed | Finishing the team report | 2024-02-07 |  | 2024-02-08 | Alia Othman | 2 | 0 | 2 | 2
OOPSIE | Flyer Design | Completed |  | 2024-02-07 |  |  | Alia Othman
OOPSIE | Team Report | Completed | Team Report | 2024-05-08 |  | 2024-02-11 | Alia Othman | 3 |  | 2 | 2
OOPSIE | Team Report | Completed | Team Report | 2024-05-08 |  | 2024-02-12 | Alia Othman | 1 |  | 2 | 2
OOPSIE | Team Report | Completed | Team Report | 2024-05-08 |  | 2024-02-18 | Alia Othman | 2 |  | 2 | 3
OOPSIE | Team Report | Completed | Team Report | 2024-05-08 |  | 2024-02-22 | Alia Othman | 2 |  | 2 | 4
OOPSIE | Team Report | Completed | Team Report | 2024-05-08 |  | 2024-02-23 | Alia Othman |  | 10 | 2 | 4
OOPSIE | Team Report | Completed | Creating the team report | 2024-05-08 |  | 2024-03-24 | Alia Othman | 3 |  | 3 | 6
OOPSIE | Team Report | Completed | Update the team report | 2024-05-08 |  | 2024-04-15 | Alia Othman | 2 |  | 4 | 8
OOPSIE | Team Report | Completed | Finishing the team report | 2024-05-08 |  | 2024-04-23 | Alia Othman | 1 |  | 5 | 8
OOPSIE | Database | Completed | Access Database | 2024-02-29 |  | 2024-03-01 | Alia Othman | 2 |  | 3 | 4
OOPSIE | Database | Completed | Creating a Form | 2024-02-29 |  | 2024-03-05 | Alia Othman | 2 |  | 3 | 4
OOPSIE | Database | Completed | Creating the query | 2024-02-29 |  | 2024-03-12 | Alia Othman | 2 |  | 3 | 5
OOPSIE | Database | Completed | Finishing the Databases | 2024-02-29 |  | 2024-03-17 | Alia Othman | 3 |  | 3 | 5
OOPSIE | Brochure Design | Completed | Creating the Brochure | 2024-03-27 |  | 2024-03-14 | Alia Othman | 3 |  | 3 | 5
OOPSIE | Brochure Design | Completed | Creating the Brochure | 2024-03-27 |  | 2024-03-17 | Alia Othman | 2 |  | 3 | 5
OOPSIE | Brochure Design | Completed | Creating Brochure | 2024-03-27 |  | 2024-03-19 | Alia Othman | 1 | 30 | 3 | 5
OOPSIE | Brochure Design | Completed | Creating the Brochure | 2024-03-27 |  | 2024-03-20 | Alia Othman | 3 | 30 | 3 | 5
OOPSIE | Brochure Design | Completed | Finishing the Broschure | 2024-03-27 |  | 2024-03-23 | Alia Othman | 1 | 30 | 3 | 6
OOPSIE | Testing the website | Completed | Testing the website | 2024-04-17 |  | 2024-04-14 | Alia Othman | 2 |  | 4 | 8
OOPSIE | Testing the website | Completed | Testing the website | 2024-04-17 |  | 2024-04-16 | Alia Othman | 1 |  | 4 | 8
OOPSIE | Testing the website | Completed | Testing the website | 2024-04-17 |  | 2024-04-24 | Alia Othman | 1 |  | 5 | 8
OOPSIE | Wireframe/Layout and Color Scheme | Completed | Layout/wireframe and color scheme brainstorming | 2024-02-07 |  | 2024-01-26 | Katherine Robbins | 1 |  | 1 | 1
OOPSIE | Wireframe/Layout and Color Scheme | Completed | Layout/wireframe and color scheme research | 2024-02-07 |  | 2024-01-28 | Katherine Robbins | 1 |  | 1 | 1
OOPSIE | Wireframe/Layout and Color Scheme | Completed | Color Scheme | 2024-02-07 |  | 2024-02-03 | Katherine Robbins | 1 |  | 1 | 2
OOPSIE | Wireframe/Layout and Color Scheme | Completed | Color Scheme/Layourt | 2024-02-07 |  | 2024-02-04 | Katherine Robbins | 1 | 30 | 1 | 2
OOPSIE | Wireframe/Layout and Color Scheme | Completed | Researching Color Scheme / Wireframe (personal) | 2024-02-07 |  | 2024-01-30 | Katherine Robbins | 1 |  | 1 | 1
OOPSIE | Wireframe/Layout and Color Scheme | Completed | Finalizing Color Scheme / Layout | 2024-02-07 |  | 2024-02-06 | Katherine Robbins | 2 |  | 1 | 2
OOPSIE | Wireframe/Layout and Color Scheme | Completed | Adjusting Bootstrap Layout | 2024-02-07 |  | 2024-02-27 | Katherine Robbins | 3 |  | 2 | 4
OOPSIE | Website Template Edit | In Progress | Editing Template | 2024-02-28 |  | 2024-02-12 | Katherine Robbins | 2 |  | 2 | 2
OOPSIE | Website Template Edit | In Progress | researched possible stock photos | 2024-02-28 |  | 2024-02-13 | Katherine Robbins | 1 |  | 2 | 2
OOPSIE | Website Template Edit | In Progress | continued editing of template | 2024-02-28 |  | 2024-02-13 | Katherine Robbins | 2 |  | 2 | 2
OOPSIE | Website Template Edit | In Progress | Website Work | 2024-02-28 |  | 2024-02-16 | Katherine Robbins | 1 |  | 2 | 3
OOPSIE | Website Template Edit | In Progress | template meeting | 2024-02-28 |  | 2024-02-16 | Katherine Robbins | 1 |  | 2 | 3
OOPSIE | Website Template Edit | In Progress | template editing | 2024-02-28 |  | 2024-02-18 | Katherine Robbins | 1 | 30 | 2 | 3
OOPSIE | Website Template Edit | In Progress | Edited home page | 2024-02-28 |  | 2024-02-20 | Katherine Robbins | 1 |  | 2 | 3
OOPSIE | Website Template Edit | In Progress | Edited home page | 2024-02-28 |  | 2024-02-23 | Katherine Robbins | 1 |  | 2 | 4
OOPSIE | Website Template Edit | In Progress | Edited home page | 2024-02-28 |  | 2024-02-26 | Katherine Robbins | 1 |  | 2 | 4
OOPSIE | Website Template Edit | In Progress | Edited home page | 2024-02-28 |  | 2024-02-27 | Katherine Robbins | 2 |  | 2 | 4
OOPSIE | Website Template Edit | In Progress | editing about page | 2024-02-28 |  | 2024-03-03 | Katherine Robbins | 1 |  | 3 | 4
OOPSIE | Website Template Edit | In Progress | editing about page | 2024-02-28 |  | 2024-03-05 | Katherine Robbins | 1 |  | 3 | 4
OOPSIE | Website Template Edit | In Progress | Learn more & home page edits | 2024-02-28 |  | 2024-03-19 | Katherine Robbins | 3 | 0 | 3 | 5
OOPSIE | Website Template Edit | In Progress | Website Template Work | 2024-02-28 |  | 2024-03-14 | Katherine Robbins | 2 |  | 3 | 5
OOPSIE | Website Template Edit | In Progress | Web Design Meeting | 2024-02-28 |  | 2024-02-18 | Katherine Robbins | 1 |  | 2 | 3
OOPSIE | Website Template Edit | In Progress | Modifying Pages | 2024-02-28 |  | 2024-03-19 | Katherine Robbins | 2 |  | 3 | 5
OOPSIE | Website Template Edit | In Progress | home page | 2024-02-28 |  | 2024-03-25 | Katherine Robbins | 3 |  | 3 | 6
OOPSIE | Website Template Edit | In Progress | Updated Colors / Sections | 2024-02-28 |  | 2024-04-03 | Katherine Robbins | 2 |  | 4 | 6
OOPSIE | Website Template Edit | In Progress | home page edits | 2024-02-28 |  | 2024-04-02 | Katherine Robbins | 3 |  | 4 | 6
OOPSIE | Website Template Edit | In Progress | learn more page edits & some home page edits | 2024-02-28 |  | 2024-04-08 | Katherine Robbins | 3 |  | 4 | 7
OOPSIE | Website Template Edit | In Progress | Template Work | 2024-02-28 |  | 2024-04-09 | Katherine Robbins | 3 |  | 4 | 7
OOPSIE | Website Template Edit | In Progress | almost done! | 2024-02-28 |  | 2024-04-13 | Katherine Robbins | 5 |  | 4 | 8
OOPSIE | Website Template Edit | In Progress | wrapping up | 2024-02-28 |  | 2024-04-19 | Katherine Robbins | 3 |  | 5 | 8
OOPSIE | Website Template Edit | In Progress | Finishing touches | 2024-02-28 |  | 2024-04-23 | Katherine Robbins | 3 |  | 5 | 8
OOPSIE | ERD Construction | Completed | Worked on identifying data requirements | 2024-02-14 |  | 2024-01-24 | Rachel Owen | 2 | 30 | 1 | 1
OOPSIE | ERD Construction | Completed | ERD construction | 2024-02-14 |  | 2024-01-24 | Rachel Owen | 2 | 30 | 1 | 1
OOPSIE | ERD Construction | Completed | Completed First Draft of ERD | 2024-02-14 |  | 2024-01-26 | Rachel Owen | 1 |  | 1 | 1
OOPSIE | ERD Construction | Completed | ERD construction | 2024-02-14 |  | 2024-01-26 | Rachel Owen | 1 |  | 1 | 1
OOPSIE | ERD Construction | Completed | Worked on identifying data requirements | 2024-02-14 |  | 2024-01-24 | Rachel Owen | 1 |  | 1 | 1
OOPSIE | ERD Construction | Completed | Comitted final draft of ERD to Repository | 2024-02-14 |  | 2024-01-28 | Rachel Owen | 0 | 30 | 1 | 1
OOPSIE | ERD Construction | Completed | Reevaluated Data Requirements, Expanded Scope | 2024-02-14 |  | 2024-01-31 | Rachel Owen | 1 | 30 | 1 | 1
OOPSIE | ERD Construction | Completed | New Draft of ERD Completed | 2024-02-14 |  | 2024-02-02 | Rachel Owen | 1 |  | 1 | 2
OOPSIE | ERD Construction | Completed | ERD construction | 2024-02-14 |  | 2024-02-02 | Rachel Owen | 1 |  | 1 | 2
OOPSIE | ERD Construction | Completed | Reviewed And Made Final Adjustments To ERD | 2024-02-14 |  | 2024-02-04 | Rachel Owen |  | 30 | 1 | 2
OOPSIE | SOURCE CONTROL | Completed | Successfully Cloned And Merged Repository | 2024-01-31 |  | 2024-01-28 | Rachel Owen | 3 | 30 | 1 | 1
OOPSIE | SOURCE CONTROL | Completed | Dalia Ghanem | 2024-01-31 |  | 2024-02-13 | Rachel Owen | 1 | 30 | 2 | 2
OOPSIE | MVC Application | In Progress | Added EntityFramework and Connected Database to the Project | 2024-06-17 |  | 2024-02-16 | Rachel Owen |  | 30 | 2 | 3
OOPSIE | MVC Application | In Progress | Created Scaffolded Areas | 2024-06-17 |  | 2024-02-16 | Rachel Owen | 1 |  | 2 | 3
OOPSIE | MVC Application | In Progress | Added Lumen Bootstrap Theme | 2024-06-17 |  | 2024-02-26 | Rachel Owen | 3 |  | 2 | 4
OOPSIE | MVC Application | In Progress | Added Site Navigation | 2024-06-17 |  | 2024-03-01 | Rachel Owen | 2 |  | 3 | 4
OOPSIE | MVC Application | In Progress | Drafted Potential Designs | 2024-06-17 |  | 2024-03-03 | Rachel Owen | 1 |  | 3 | 4
OOPSIE | MVC Application | In Progress | Drafted design plans | 2024-06-17 |  | 2024-03-03 | Rachel Owen | 1 |  | 3 | 4
OOPSIE | MVC Application | In Progress | Deployed Application to School Server | 2024-06-17 |  | 2024-03-06 | Rachel Owen |  | 30 | 3 | 4
OOPSIE | MVC Application | In Progress | Login is now functional | 2024-06-17 |  | 2024-03-08 | Rachel Owen | 1 | 30 | 3 | 5
OOPSIE | MVC Application | In Progress | Added some documentation | 2024-06-17 |  | 2024-03-09 | Rachel Owen |  | 30 | 3 | 5
OOPSIE | MVC Application | In Progress | Met with Dalia to discuss message stuff | 2024-06-17 |  | 2024-03-27 | Rachel Owen |  | 20 | 3 | 6
OOPSIE | MVC Application | In Progress | Debugging | 2024-06-17 |  | 2024-03-27 | Rachel Owen | 1 |  | 3 | 6
OOPSIE | MVC Application | In Progress | User Search and Condition Database | 2024-06-17 |  | 2024-04-13 | Rachel Owen | 9 |  | 4 | 8
OOPSIE | MVC Application | In Progress | Search by Condition | 2024-06-17 |  | 2024-04-15 | Rachel Owen | 2 |  | 4 | 8
OOPSIE | Message System | Completed | Trying my best | 2024-04-20 |  | 2024-03-18 | Rachel Owen | 1 |  | 3 | 5
OOPSIE | Message System | Completed | added a message class! | 2024-04-20 |  | 2024-03-18 | Rachel Owen |  | 30 | 3 | 5
OOPSIE | Message System | Completed | Created Read/Unread Flag | 2024-04-20 |  | 2024-03-24 | Rachel Owen | 2 |  | 3 | 6
OOPSIE | Message System | Completed | Messages are working and posting | 2024-04-20 |  | 2024-03-24 | Rachel Owen | 2 |  | 3 | 6
OOPSIE | Message System | Completed | Messages Can Be Sent! | 2024-04-20 |  | 2024-03-30 | Rachel Owen | 3 |  | 4 | 6
OOPSIE | Message System | Completed | Slight Tweaks To Layout | 2024-04-20 |  | 2024-04-03 | Rachel Owen |  | 30 | 4 | 6
OOPSIE | Message System | Completed | Replies! | 2024-04-20 |  | 2024-04-06 | Rachel Owen | 3 | 30 | 4 | 7
OOPSIE | Message System | Completed | Replies to Replies! | 2024-04-20 |  | 2024-04-07 | Rachel Owen | 5 |  | 4 | 7
OOPSIE | Message System | Completed | Nested Replies | 2024-04-20 |  | 2024-04-08 | Rachel Owen | 6 |  | 4 | 7
OOPSIE | User Profiles | Completed | Made User Partial Class | 2024-04-20 |  | 2024-03-05 | Rachel Owen | 3 |  | 3 | 4
OOPSIE | User Profiles | Completed | updated and added child profiles and groups | 2024-04-20 |  | 2024-04-22 | Rachel Owen | 2 |  | 5 | 8
OOPSIE | Sprint 3 | Completed | Contributed to Presentation | 2024-03-27 |  | 2024-03-26 | Rachel Owen |  | 30 | 3 | 6
OOPSIE | Team charter | Completed | Added my info and Uploaded | 2024-01-24 |  | 2024-01-24 | Stanley Dalziel | 1 | 0 | 1 | 1
OOPSIE | Team charter | Completed | Team Charter | 2024-01-24 |  | 2024-01-24 | Stanley Dalziel | 1 |  | 1 | 1
OOPSIE | Team charter | Completed | Uploaded Charter | 2024-01-24 |  | 2024-01-24 | Stanley Dalziel |  | 15 | 1 | 1
OOPSIE | Team charter | Completed | Team Charter completed | 2024-01-24 |  | 2024-01-23 | Stanley Dalziel | 2 |  | 1 | 1
OOPSIE | Team charter | Completed | Team charter | 2024-01-24 |  | 2024-01-24 | Stanley Dalziel |  | 25 | 1 | 1
OOPSIE | Logo Design | Completed | Concept One Finished | 2024-02-07 |  | 2024-01-20 | Stanley Dalziel | 3 | 0 | 1 | 1
OOPSIE | Logo Design | Completed | Concept One | 2024-02-07 |  | 2024-01-21 | Stanley Dalziel | 3 |  | 1 | 1
OOPSIE | Logo Design | Completed | Concept Two | 2024-02-07 |  | 2024-01-22 | Stanley Dalziel | 2 |  | 1 | 1
OOPSIE | Logo Design | Completed | Concept Two | 2024-02-07 |  | 2024-01-26 | Stanley Dalziel | 2 |  | 1 | 1
OOPSIE | Logo Design | Completed | Concept Three | 2024-02-07 |  | 2024-02-04 | Stanley Dalziel | 2 |  | 1 | 2
OOPSIE | Logo Design | Completed | Logo Concept 2 | 2024-02-07 |  | 2024-01-26 | Stanley Dalziel | 2 |  | 1 | 1
OOPSIE | Logo Design | Completed | Finished Concept 3 | 2024-02-07 |  | 2024-02-04 | Stanley Dalziel | 2 |  | 1 | 2
OOPSIE | Sprint 1 Prep | Completed | Contributed Developer Resources for Sprint 1 Presentation | 2024-02-07 |  | 2024-02-06 | dalia ghanem | 2 |  | 1 | 2
OOPSIE | Sprint 1 Prep | Completed | Sprint 1 Preperation | 2024-02-07 |  | 2024-02-06 | dalia ghanem | 2 |  | 1 | 2
OOPSIE | Sprint 1 Prep | Completed | Sprint 1 Prep | 2024-02-07 |  | 2024-02-06 | dalia ghanem | 2 |  | 1 | 2
OOPSIE | Sprint 1 Prep | Completed | Sprint 1 | 2024-02-07 |  | 2024-02-06 | dalia ghanem | 2 |  | 1 | 2
OOPSIE | Sprint 1 Prep | Completed | Sprint 1 Preperation | 2024-02-07 |  | 2024-02-06 | dalia ghanem | 2 |  | 1 | 2
OOPSIE | Sprint 1 Prep | Completed | Attended and Assisted in Sprint 1 Presentation | 2024-02-07 |  | 2024-02-07 | dalia ghanem | 1 | 30 | 1 | 2
OOPSIE | Sprint 1 Prep | Completed | Presentation | 2024-02-07 |  | 2024-02-07 | dalia ghanem |  | 30 | 1 | 2
OOPSIE | Database population | Completed | Added new data into smss | 2024-02-29 |  | 2024-02-16 | dalia ghanem |  | 30 | 2 | 3
OOPSIE | Database population | Completed | Assisted in Data Population | 2024-02-29 |  | 2024-02-16 | dalia ghanem |  | 30 | 2 | 3
OOPSIE | Database population | Completed | Added new data into smss | 2024-02-29 |  | 2024-02-25 | dalia ghanem |  | 30 | 2 | 4
OOPSIE | Database population | Completed | Added account table with bobs help | 2024-02-29 |  | 2024-03-06 | dalia ghanem |  | 30 | 3 | 4
OOPSIE | Database population | Completed | Added Triggers for Parity between Accounts and Users | 2024-02-29 |  | 2024-03-06 | dalia ghanem |  | 30 | 3 | 4
OOPSIE | Database population | Completed | Added new data into smss | 2024-02-29 |  | 2024-03-07 | dalia ghanem | 1 |  | 3 | 5
OOPSIE | Database population | Completed | Adding messages data | 2024-02-29 |  | 2024-03-27 | dalia ghanem | 1 |  | 3 | 6
OOPSIE | Database population | Completed | Added levels and children info to database | 2024-02-29 |  | 2024-04-02 | dalia ghanem |  | 45 | 4 | 6
OOPSIE | Bootstrap | Completed | Connected to github and started bootstrap | 2024-02-20 |  | 2024-02-20 | dalia ghanem | 1 |  | 2 | 3
OOPSIE | Bootstrap | Completed | added bootstrap | 2024-02-20 |  | 2024-02-21 | dalia ghanem | 2 |  | 2 | 3
OOPSIE | Bootstrap | Completed | assisted in troubleshooting | 2024-02-20 |  | 2024-02-25 | dalia ghanem | 1 |  | 2 | 4
OOPSIE | Bootstrap | Completed | Bootstrap done with Bob's help | 2024-02-20 |  | 2024-02-28 | dalia ghanem |  | 30 | 2 | 4
OOPSIE | Sprint 2 Prep | Completed | Sprint 2 prep | 2024-02-28 |  | 2024-02-27 | dalia ghanem | 0 | 30 | 2 | 4
OOPSIE | Sprint 2 Prep | Completed | met with group | 2024-02-28 |  | 2024-02-27 | dalia ghanem |  | 30 | 2 | 4
OOPSIE | Sprint 2 Prep | Completed | Met with group | 2024-02-28 |  | 2024-02-27 | dalia ghanem |  | 30 | 2 | 4
OOPSIE | Sprint 2 Prep | Completed | sprint 2 prep | 2024-02-28 |  | 2024-02-27 | dalia ghanem | 1 |  | 2 | 4
OOPSIE | Sprint 2 Prep | Completed | Sprint 2 | 2024-02-28 |  | 2024-02-27 | dalia ghanem |  | 30 | 2 | 4
OOPSIE | Sprint 2 Prep | Completed | Polishing Sprint 2 Powerpoint | 2024-02-28 |  | 2024-02-28 | dalia ghanem | 1 |  | 2 | 4
OOPSIE | Sprint 2 Prep | Completed | Last minute edits to sprint presentation | 2024-02-28 |  | 2024-02-28 | dalia ghanem |  | 30 | 2 | 4
OOPSIE | Child Profiles | In Progress | Tried my best to figure out what im doing | 2024-04-05 |  | 2024-04-03 | dalia ghanem | 2 |  | 4 | 6
OOPSIE | Child Profiles | In Progress | Added partial page | 2024-04-05 |  | 2024-04-03 | dalia ghanem |  | 10 | 4 | 6
OOPSIE | Child Profiles | In Progress | Moved partial page into parent page | 2024-04-05 |  | 2024-04-04 | dalia ghanem | 1 | 30 | 4 | 7
OOPSIE | Child Profiles | In Progress | added more details but got stuck | 2024-04-05 |  | 2024-04-08 | dalia ghanem | 2 |  | 4 | 7
OOPSIE | Child Profiles | In Progress | Spiced it but but still working | 2024-04-05 |  | 2024-04-11 | dalia ghanem | 2 |  | 4 | 8
OOPSIE | Child Profiles | In Progress | CSS stuff!! | 2024-04-05 |  | 2024-04-15 | dalia ghanem | 2 |  | 4 | 8
OOPSIE | Child Profiles | In Progress | fixed child conditions and support levels in edit | 2024-04-05 |  | 2024-04-16 | dalia ghanem | 2 |  | 4 | 8

## Sheet1
Name | Task | Postion
Alia Othman | Brochure Design | Micro App
Dalia Ghnem | MRV Construction | Web Developr
Rachel Owen | MRV Construction | Web Developr
Katherine Robbins | Website Template | Web Designer
Stanley Dalziel | Website Template | Web Designer
Name | Task | Time | Progress
Micro App | Brochure Design | 10+ | Completed
Web Develop | MVC Aplication | 10+ | Completed
Web Design | Website Template | 10+ | Completed

## OOPSIE Team chart 3
Task Completed this week | Persent
Creating The Brochure | 100%
Creating the MVC Aplication | 100%
Creating The Template | 100%
Micro App | Status | Persent
Creating The flyer | Completed | 100%
Team Report | Completed | 100%
Creating the Brochure | Completed | 100%
Creating the Data Bases | Completed | 100%
Web Development | Status | Persent
Creating The ERD | Completed | 100%
Creating The MVC Aplication | Completed | 100%
Web Designer | Status | Persent
Creating The Logo | Completed | 100%
Website Template | Completed | 100%